|  | T.C. SOCIAL SCIENCES UNIVERSITY OF ANKARA SCHOOL OF FOREIGN LANGUAGES |
| --- | --- |

Date and time: 19.03.2024

Place: Dösim

Topic: Quality Assurance

Meeting Agenda

|  | Agenda |
| --- | --- |
| 1 | Administration and Management |
| 2 | Curriculum Development |
| 3 | Testing and Evaluation |
| 4 | Professional Development |
| 5 | Self-Access Center /Student support |

Decisions

|  | Decisions | Responsible person | The person who checks | Due date |
| --- | --- | --- | --- | --- |
| 1 | - Job descriptions will be shared on the website. - The sections about admin and management in the Quality Quality Assurance handbook will be revised. - Quality Assurance handbook will be compiled with the addition ofEnglish, Russian and Arabic prep details.. - DEDAK self-study report will be finalized. | DD DD NGB | NGB | 21.03.2024 31.03.2024 15.05.2024 |
| 2 | - CDU will receive feedback from department professors and students (25-29.03.2024) and write "needs analysis." report - CDU will work on "curriculum philosophy" and write it down on the curriculum file. - CDU will match the objectives with the materials. - CDU will adapt some activities in the book to practice note-taking, timed-reading, and short conversations (EPE Tasks) - The sections about CDU in the Quality Assurance handbook will be revised. - The curriculum evaluation questionnaires for Period III will be delivered to the students and instructors at SFL. - The student and instructor questionnaires for Period III will be analyzed and the results will be reported to the administrators. - DEDAK self-study report will be finalized. | ÖD | NGB | 01.05.2024 20.03.2024 25.03.2024 12.04.2024 31.03.2024 01.04.2024 10.04.2024 15.05.2024 |
| 3 | - There will be a match between the objectives/constructs and the test items. Dedak member will share the empty excel sheet with the testing members - Testing Unit will report the responses of the questionnaires and the improvements to the DEDAK member (HA). DEDAK member will keep the report files in the DEDAK evidence folder. - The sections about Testing in the Quality Assurance handbook will be revised. - DEDAK self-study report will be finalized. | HA | NGB | 21.03.2024 27.03.2024 31.03.2024 15.05.2024 |
| 3 | - PDU coordinator will finalize the analysis of teacher assessment forms with the help of the Vice-Director and share them with the instructors individually. - The PDU coordinator will prepare an orientation presentation for the new faculty members and conduct orientation sessions with the participation of other unit heads when the new instructors start to work in our institution. - The sections about PDU in the Quality Assurance handbook will be revised. - DEDAK self-study report will be finalized. | MW | NGB | 29.03.2024 15.04.2024 31.03.2024 15.07.2024 |
| 4 | - The sections about SAC in the Quality Assurance handbook will be revised. - Objective matching tasks will be completed. - DEDAK self-study report will be finalized. | MŞ | NGB | 31.03.2024 05.04.2024 15.05.2024 |

Participants

| Name and Surname | Title | Unit | Signature |
| --- | --- | --- | --- |
| Nur Gedik Bal | Vice-Head of the Department | Management |  |
| Davut Doğan | Vice-Director of the School | Administration |  |
| Öznur Demirkaya | Curriculum Coordinator | CDU |  |
| Havanur Aytaş | Testing DEDAK Member | Testing |  |